## ACTIVITY LOG SHEET(13)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 12
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Cost Analysis |  | I | 2018-10-09 | 8:00 | 10:00 |  | 2
Prepared Presentation Script |  | I | 2018-10-14 | 09:00am | 10:00AM |  | 1
Practiced and recorded presentation |  | I | 2018-10-14 | 10:00AM | 11:00Am |  | 1
Reviewed and edited final assignment |  | I | 2018-10-16 | 6:00PM | 7:00PM |  | 1
Total | [5 empty] | 0 | 5
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(12)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 11
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Created PHP/Js to get database stats |  | I | 43377 | 2:00PM | 3:00PM |  | 1
Moved all individaul pages into JS. |  | I | 43379 | 7:00AM | 9:00 |  | 2
Added ability to select multiple root folders |  | I | 43379 | 10:00AM | 12:00 |  | 3
Added buttons to remove root folders from database and tested. |  | I | 43380 | 8:00AM | 10:00AM |  | 2
Total | [5 empty] | 0 | 8
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(11)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 10
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Added code to read user rating metadata and tested |  | I | 2018-09-27 | 12:00PM | 1:00PM |  | 1
Altered code to add photo year to display |  | I | 2018-09-29 | 7:00AM | 8:30AM |  | 1.5
Added code to allow user to select time sort order |  | I | 2018-09-29 | 8:30AM | 9:30 |  | 1
Tested and adjusted sort and display code |  | I | 2018-09-29 | 9:30AM | 10:00AM |  | 0.5
Created a select form example showing peer how to use XHR to dynamically adjust selection options. |  | I | 2018-09-30 | 07:00AM | 10:00AM |  | 3
Reviewed Peers work on advanced search form and debugged errors |  | I | 2018-09-30 | 3:00PM | 3:30PM |  | 0.5
Created final project template |  | I | 2018-10-01 | 8:30 | 9:00AM |  | 0.5
Reviewed assignment 3 specifications and added outstanging tasks to the Projects task management sheet. |  |  | 2018-10-01 | 9:30 | 10:00AM |  | 0.5
Total | [5 empty] | 0 | 8.5
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(10)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 9
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Created Script to delete database and created javascript function to call php |  | I | 2018-09-21 | 12:00PM | 1:00PM |  | 1
Researched PEL |  | I | 2018-09-22 | 8:00AM | 10:00AM |  | 2
Added and refactored code to get_meta.php so displays extra metadata. |  | I | 2018-09-22 | 10:00AM | 11:00AM |  | 1
Added code to edit the new metadata fields. |  | I | 2018-09-22 | 2:00PM | 3:00PM |  | 1
Tested and troubleshoot new code |  | I | 2018-09-22 | 4:00PM | 5:00PM |  | 1
Git admin |  | I | 2018-09-22 | 3:00PM | 4:00PM |  | 1
Added code to allow user to change drive. |  | I | 2018-09-23 | 08:00AM | 10:00AM |  | 2
Total | [5 empty] | 0 | 9
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(9)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 8
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Created a initial Advanced search script in php |  | I | 2018-09-14 | 16:00PM | 17:00PM |  | 1
Tested a initial Advanced search script in php |  | I | 2018-09-14 | 17:00PM | 18:00PM |  | 1
Researched methods to retreive used folder |  | I | 2018-09-15 | 09:00AM | 10:00AM |  | 2
Implemented browse.php script to return all directories in folder. |  | I | 2018-09-15 | 2:00PM | 3:00PM |  | 1
Implemented js code to use ajax to call browse and display subFolders |  | G | 2018-09-15 | 6:00PM | 6:30PM |  | 1
Tested code and adjusted code |  | G | 2018-09-15 | 09:00AM | 09:30AM |  | 1
Discused browser search code and tested on group computers. Fixed small erros |  | I | 2018-09-16 | 09:00AM | 10:00AM | 1
Total | [5 empty] | 1 | 7
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(8)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 7
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Researched how to retreive and store thumbnail images |  | I | 2018-09-05 | 09:00AM | 11:00PM |  | 2
Implemented code to extract and store thumbnail images |  | I | 2018-09-05 | 11:00AM | 12:00PM |  | 1
Altered code so that displayed thumbnails instead of full images |  | I | 2018-09-05 | 01:00PM | 02:00PM |  | 1
Tested and adjusted new code |  | I | 2018-09-05 | 2:00AM | 3:00PM |  | 1
Team Meeting |  | G | 2018-09-07 | 6:00PM | 6:30PM | 0.5
Group Test and adjust code |  | G | 2018-09-08 | 09:00AM | 09:30AM | 0.5
Implemented the remainer of the DB |  | I | 2018-09-08 | 09:30AM | 10:00AM |  | 0.5
Updated the search and db update code to match the scheme |  | I | 2018-09-08 | 12:00PM | 2:00PM |  | 2
Tested and adjusted the new code |  | I | 2018-09-08 | 2:00PM | 3:00PM |  | 1
Group Test and adjust code |  | G | 2018-09-09 | 9:00AM | 09:30AM | 0.5
Add task to Project Sheet |  | I | 2018-09-09 | 9:30AM | 10:00AM |  | 0.5
Total | [5 empty] | 1.5 | 9
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(7)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 6
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
DB discussions |  | G | 2018-08-30 | 07:00PM | 08:00PM | 1
Researched JPEG metadata editing and PEL |  | I | 2018-09-01 | 9:00AM | 12:00PM |  | 3
Code the metadata editor script |  | I | 2018-09-01 | 01:00PM | 03:00PM |  | 2
Code the XHR calls in Javascript |  | I | 2018-09-02 | 9:00AM | 11:00PM |  | 2
Test and rectify metadata editor and Javascript together |  | I | 2018-09-02 | 11:00 | 01:00PM |  | 2
Total | [5 empty] | 1 | 9
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(6)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 5
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Tested on Windows using XAMPP and fixed errors |  | I | 2018-08-25 | 08:00AM | 12:00AM |  | 4
Coded metadata reader script |  | I | 2018-08-26 | 08:00AM | 11:00AM |  | 3
Coded XHR funtion in JS |  | I | 2018-08-26 | 12:00PM | 02:00PM |  | 2
Test JS and metadata reader |  | I | 2018-08-26 | 02:00PM | 03:00PM |  | 1
Total | [5 empty] | 0 | 10
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(5)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 4
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Code the initial file scanner |  | I | 2018-08-18 | 08:00AM | 12:00AM |  | 4
Code the initial photo retriever |  | I | 2018-08-18 | 1:00PM | 4:00PM |  | 3
Code the XHR functions in JS |  | I | 2018-08-19 | 08:00AM | 11:00AM |  | 3
Code the basic search script |  | I | 2018-08-19 | 1:00PM | 3:00PM |  | 2
Total | [5 empty] | 0 | 12
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(4)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 3
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Research Data base |  | I | 2018-08-12 | 08:00AM | 9:00PM |  | 1
Code the initiral data base script |  | I | 2018-08-15 | 08:00AM | 11:00AM |  | 3
Final Review/draft Ass2 |  | I | 2018-08-15 | 12:00:00 PM | 3:00PM |  | 3
Total | [5 empty] | 0 | 7
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(3)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 2
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Meeting With Supervisor |  | G | 2018-07-30 | 18:30 | 19:20 | 1
WBS |  | I | 2018-08-04 | 8:00 | 11:00 |  | 2
GITHUB ACCOUNT |  | I | 2018-08-03 | 6:00PM | 7:00PM |  | 1
Operational processes |  | I | 2018-08-04 | 11:00AM | 1:00PM |  | 2
Gaunt Chart |  | I | 2018-08-04 | 8:00AM | 12:00PM |  | 2
Meeting Minutes |  | I | 2018-08-02 | 5:00PM | 7:00PM |  | 2
Total | [5 empty] | 1 | 9
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET(2)
ACTIVITY LOG SHEET
Name | Gregory Jones |  |  |  | Week |  | 1
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Risk Management |  | I | 2018-07-21 | 8:00 | 10:00 |  | 2
Project Research |  | I | 2018-07-21 | 10:00 | 11:00 |  | 1
WBS |  | I | 2018-07-21 | 11:00 | 12:00 |  | 1
Team Principles |  | I | 2018-07-22 | 7:00 | 9:00 |  | 2
Non-Compliance rules |  | I | 2018-07-22 | 9:00 | 11:00 |  | 2
Operational Processes |  | I | 2018-07-22 | 11:00 | 12:00 |  | 1
Total | [5 empty] | 0 | 9
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.