## Greg
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 5 | 1 | 3 |  |  |  |  | 9
Week 2 | 3 | 3 | 4 |  |  |  |  | 10
Week 3 |  |  | 3 | 1 | 3 |  |  | 7
Week 4 |  |  |  |  | 12 |  |  | 12
Week 5 |  |  |  |  | 10 |  |  | 10
Week 6 |  | 3 |  | 1 | 6 |  |  | 10
Week 7 |  | 2 |  |  | 7.5 | 1 |  | 10.5
Week 8 |  | 2 |  |  | 5 |  |  | 7
Week 9 |  | 2 |  |  | 6 | 1 |  | 9
Week 10 |  |  |  |  | 8 | 0.5 |  | 8.5
Week 11 |  |  |  |  | 8 |  | 0.5 | 8.5
Week 12 | [6 empty] | 2 | 2
Week 13
Total | 8 | 13 | 10 | 2 | 65.5 | 2.5 | 2.5 | 103.5

## Ryan
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 3 | 0.5 | [5 empty] | 3.5
Week 2 | 1 | 2 | [5 empty] | 3
Week 3 |  |  | 1.5 |  |  |  |  | 1.5
Week 4 |  |  | 4 |  |  |  |  | 4
Week 5 |  |  | 3 |  |  |  |  | 3
Week 6 | 0.5 |  |  | 1 |  |  |  | 1.5
Week 7 |  |  |  | 11 |  |  |  | 11
Week 8 |  |  |  | 5 | 2 |  |  | 7
Week 9 |  |  |  | 3 | 2.5 |  |  | 5.5
Week 10 |  |  |  |  | 8 |  |  | 8
Week 11 |  |  |  |  | 4.5 | 0.5 |  | 5
Week 12 |  |  |  | 2.5 | 3 | 2.5 |  | 8
Week 13
Total | 4.5 | 2.5 | 8.5 | 22.5 | 20 | 3 | 0 | 61

## Andrew
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 3 | 2.5 | [5 empty] | 5.5
Week 2 |  | 1 |  | 5 | 2 |  |  | 8
Week 3 |  |  | 9.5 |  |  |  |  | 9.5
Week 4 | 0.5 |  | 6 |  |  |  |  | 6.5
Week 5 | 4 | [6 empty] | 4
Week 6 | 0.5 | 2 | [5 empty] | 2.5
Week 7 |  | 1.5 |  | 7 | 3 | 1 |  | 12.5
Week 8 |  | 2 |  | 4 | 1 |  |  | 7
Week 9 |  |  |  | 4 | 2 |  |  | 6
Week 10 |  |  |  | 5 | 1 |  |  | 6
Week 11 |  |  |  | 3.5 | 0.5 |  |  | 4
Week 12 | [7 empty] | 0
Week 13
Total | 8 | 9 | 15.5 | 28.5 | 9.5 | 1 | 0 | 71.5

## Isaac
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 1.25 | 1 | [5 empty] | 2.25
Week 2 |  | 1.5 |  |  |  | 0.25 |  | 1.75
Week 3 |  | 1.5 | 1.5 |  |  | 0.25 |  | 3.25
Week 4 |  | 0.25 | 3 |  |  | 4.25 |  | 7.5
Week 5 |  | 0.25 | 3 |  |  | 0.25 |  | 3.5
Week 6 | 3 | 0.25 |  |  |  | 0.25 |  | 3.5
Week 7 | 2 | 0.25 |  |  |  | 0.75 |  | 3
Week 8 |  | 0.25 |  | 3 | 0.5 | 0.75 |  | 4.5
Week 9 |  | 0.25 |  | 6 | 2 | 0.75 |  | 9
Week 10 |  | 0.25 |  | 3 | 2 | 0.25 |  | 5.5
Week 11 |  | 0.25 |  | 4 | 2 | 0.25 |  | 6.5
Week 12 |  | 1 |  | 1 | 2 | 3 |  | 7
Week 13
Total | 6.25 | 7 | 7.5 | 17 | 8.5 | 11 | 0 | 57.25
| 6.25 | 7 | 7.5 | 17 | 8.5 | 11 | 0
| 6.25 | 7 | 7.5 | 17 | 8.5 | 11 | 0
6.25
7
7.5
17
8.5
11
0

## Total Hrs
Week Number | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 12.25 | 5 | 3 | 0 | 0 | 0 | 0 | 20.25
Week 2 | 4 | 7.5 | 4 | 5 | 2 | 0.25 | 0 | 22.75
Week 3 | 0 | 1.5 | 15.5 | 1 | 3 | 0.25 | 0 | 21.25
Week 4 | 0.5 | 0.25 | 13 | 0 | 12 | 4.25 | 0 | 30
Week 5 | 4 | 0.25 | 6 | 0 | 10 | 0.25 | 0 | 20.5
Week 6 | 4 | 5.25 | 0 | 2 | 6 | 0.25 | 0 | 17.5
Week 7 | 2 | 3.75 | 0 | 18 | 10.5 | 2.75 | 0 | 37
Week 8 | 0 | 4.25 | 0 | 12 | 8.5 | 0.75 | 0 | 25.5
Week 9 | 0 | 2.25 | 0 | 13 | 12.5 | 1.75 | 0 | 29.5
Week 10 | 0 | 0.25 | 0 | 8 | 19 | 0.75 | 0 | 28
Week 11 | 0 | 0.25 | 0 | 7.5 | 15 | 0.75 | 0.5 | 24
Week 12 | 0 | 1 | 0 | 3.5 | 5 | 5.5 | 2 | 17
Week 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 26.75 | 31.5 | 41.5 | 70 | 103.5 | 17.5 | 2.5 | 293.25
| 15 | 20 | 32 | 12 | 201 | 60 | 37 | 377

## Sheet1
ID | Phase | Hours(4) | Cost (Business Analyst Rate(1)) | Cost (Programmer Rate(2)) | Cost (Project Manager Rate(3)) | Total Phase Cost | PM Hours | BA/ Programmer Hours | ID | Phase | Hours(4) | Cost (Business Analyst Rate(1)) | Cost (Programmer Rate(2)) | Cost (Project Manager Rate(3)) | Total Phase Cost
1 | Initialising | 26.75 | 997.325 | 0 | 505.8125 | 3403.2 | 6.25 | 20.5 | 1 | Initialising | 15 | 2189.25 | 0 | 1213.95 | 3403.2
2 | Discover and understand the details of the problem | 31.5 | 1191.925 | 0 | 566.51 | 4537.6 | 7 | 24.5 | 2 | Discover and understand the details of the problem | 20 | 2919 | 0 | 1618.6 | 4537.6
3 | Create the project plan. | 41.5 | 1654.1 | 0 | 606.975 | 7260.16 | 7.5 | 34 | 3 | Create the project plan. | 32 | 4670.4 | 0 | 2589.76 | 7260.16
4 | Design Components | 70 | 0 | 1855 | 1375.81 | 1680 | 17 | 53 | 4 | Design Components | 12 | 0 | 1680 | 0 | 1680
5 | Build all the program components, integrate and test. | 103.5 | 0 | 3325 | 687.905 | 25200 | 8.5 | 95 | 5 | Build all the program components, integrate and test. | 240 | 0 | 25200 | 0 | 25200
6 | Monitoring and Controlling | 17.5 | 316.225 | 0 | 890.23 | 4764.48 | 11 | 6.5 | 6 | Monitoring and Controlling | 21 | 3064.95 | 0 | 1699.53 | 4764.48
7 | Deploy | 2.5 | 121.625 | 0 | 0 | 8394.56 | 0 | 2.5 | 7 | Deploy | 37 | 5400.15 | 0 | 2994.41 | 8394.56
Totals |  | 293.25 | 4281.2 | 5180 | 4633.2425 | 14094.4425 |  |  | Totals |  | 377 | 18243.75 | 38556 | 10116.25 | 66916
Notes: | [6 empty] | 3400 | 17494.4425 | Notes:
1. Business Analyst Hourly Rate-$48.65 (PayScale 2018). | [7 empty] | 2634.5575 | 1. Business Analyst Hourly Rate-$48.65 (PayScale 2018).
2. Programmer Hourly Rate-$35(PayScale 2018). | [8 empty] | 2. Programmer Hourly Rate-$35(PayScale 2018).
3. Project Manager Hourly Rate-$80.93(PayScale 2018). | [8 empty] | 3. Project Manager Hourly Rate-$80.93(PayScale 2018).
4. Phase hours sourced from Task Log Summary, refer Appendix XX. | [8 empty] | 4. Phase hours sourced from WBS, refer Table 1.
|  |  | 48.65 | 35 | 80.93 | [5 empty] | 377
0
17494.4425
16729
3400
20129

## Sheet2
0.42917 | 583.3333 | 72