## Greg
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 2.5 | [6 empty] | 2.5 |  | 2018-07-16 | 2018-07-22 | 1
Week 2 | 5 | 1 | 3 |  |  |  |  | 9 |  | 2018-07-23 | 2018-07-29 | 2
Week 3 | 3 | 3 | 4 |  |  |  |  | 10 |  | 2018-07-30 | 2018-08-05 | 3
Week 4 |  |  | 3 | 1 | 3 |  |  | 7 |  | 2018-08-06 | 2018-08-12 | 4
Week 5 |  |  |  |  | 12 |  |  | 12 |  | 2018-08-13 | 2018-08-19 | 5
Week 6 |  |  |  |  | 10 |  |  | 10 |  | 2018-08-20 | 2018-08-26 | 6
Week 7 |  | 3 |  | 1 | 6 |  |  | 10 |  | 2018-08-27 | 2018-09-02 | 7
Week 8 |  | 2 |  |  | 7.5 | 1 |  | 10.5 |  | 2018-09-03 | 2018-09-09 | 8
Week 9 |  | 2 |  |  | 5 | 1 |  | 8 | 8 | 2018-09-10 | 2018-09-16 | 9
Week 10 |  | 2 |  |  | 6 | 1 |  | 9 |  | 2018-09-17 | 2018-09-23 | 10
Week 11 |  |  |  |  | 7.5 |  | 1 | 8.5 |  | 2018-09-24 | 2018-09-30 | 11
Week 12 |  |  |  |  | 8 |  |  | 8 |  | 2018-10-01 | 2018-10-07 | 12
Week 13 | [6 empty] | 5 | 5 |  | 2018-10-08 | 2018-10-14 | 13
Week 14 | [6 empty] | 3 | 3 |  | 2018-10-15 | 2018-10-21
Total | 10.5 | 13 | 10 | 2 | 65 | 3 | 6 | 107

## Ryan
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 1 |  |  |  |  | 0.25 |  | 1.25
Week 2 | 1 |  |  |  |  | 3.25 |  | 4.25
Week 3 |  | 1.5 |  |  |  | 0.25 |  | 1.75
Week 4 |  |  | 3 |  |  | 1.25 |  | 4.25
Week 5 |  |  | 1 |  |  | 2.25 |  | 3.25
Week 6 |  |  |  | 0.5 |  | 1.25 |  | 1.75
Week 7 |  | 10 |  |  |  | 1.25 |  | 11.25
Week 8 |  | 6 |  |  | 2 | 0.25 |  | 8.25
Week 9 |  | 3 |  |  | 3 | 0.25 |  | 6.25
Week 10 |  |  |  |  | 8 | 0.25 |  | 8.25
Week 11 |  |  |  |  | 4.5 | 0.25 |  | 4.75
Week 12 |  |  |  | 2.5 | 3 | 2.75 |  | 8.25
Week 13 | [5 empty] | 2.75 | 3 | 5.75
Week 14 | [5 empty] | 2.75 | 2 | 4.75
Total | 2 | 20.5 | 4 | 3 | 20.5 | 19 | 5 | 74

## Andrew
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 3 | 2.5 | [5 empty] | 5.5
Week 2 |  | 1 |  | 5 | 2 |  |  | 8
Week 3 |  |  | 9.5 |  |  |  |  | 9.5
Week 4 | 0.5 |  | 6 |  |  |  |  | 6.5
Week 5 | 4 | [6 empty] | 4
Week 6 | 0.5 | 2 | [5 empty] | 2.5
Week 7 |  | 1.5 |  | 7 | 3 | 1 |  | 12.5
Week 8 |  | 2 |  | 4 | 1 |  |  | 7
Week 9 |  |  |  | 4 | 2 |  |  | 6
Week 10 |  |  |  | 5 | 1 |  |  | 6
Week 11 |  |  |  | 3.5 | 0.5 |  |  | 4
Week 12 |  |  |  |  | 4 |  |  | 4
Week 13 | [6 empty] | 2.5 | 2.5
Week 14 | [6 empty] | 1.5 | 1.5
Total | 8 | 9 | 15.5 | 28.5 | 13.5 | 1 | 4 | 79.5

## Isaac
Column1 | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total | Column2
Week 1 | 1.25 | 1 | [5 empty] | 2.25 | 1
Week 2 |  | 1.5 |  |  |  | 0.25 |  | 1.75 | 2
Week 3 |  | 1.5 | 1.5 |  |  | 0.25 |  | 3.25 | 3
Week 4 |  | 0.25 | 3 |  |  | 4.25 |  | 7.5 | 4
Week 5 |  | 0.25 | 3 |  |  | 0.25 |  | 3.5 | 5
Week 6 | 3 | 0.25 |  |  |  | 0.25 |  | 3.5 | 6
Week 7 | 2 | 0.25 |  |  |  | 0.75 |  | 3 | 7
Week 8 |  | 0.25 |  | 3 | 0.5 | 0.75 |  | 4.5 | 8
Week 9 |  | 0.25 |  | 6 | 2 | 0.75 |  | 9 | 9
Week 10 |  | 0.25 |  | 3 | 2 | 0.25 |  | 5.5 | 10
Week 11 |  | 0.25 |  | 4 | 2 | 0.25 |  | 6.5 | 11
Week 12 |  | 1 |  | 1 | 2 | 3 |  | 7 | 12
Week 13 | [5 empty] | 0.5 | 5 | 5.5 | 13
Week 14 | [5 empty] | 1.5 | 6.25 | 7.75 | 14
Total | 6.25 | 7 | 7.5 | 17 | 8.5 | 13 | 11.25 | 70.5
| 6.25 | 7 | 7.5 | 17 | 8.5 | 11 | 0
| 6.25 | 7 | 7.5 | 17 | 8.5 | 11 | 0
6.25
7
7.5
17
8.5
11
0

## Contributions
Name | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy
Greg | 10.5 | 13 | 10 | 2 | 65 | 3 | 6
Ryan | 2 | 20.5 | 4 | 3 | 20.5 | 19 | 5
Andrew | 8 | 9 | 15.5 | 28.5 | 13.5 | 1 | 4
Isaac | 6.25 | 7 | 7.5 | 17 | 8.5 | 13 | 11.25
Total | 26.75 | 49.5 | 37 | 50.5 | 107.5 | 36 | 26.25
Name | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy
Greg | 39.25% | 26.26% | 27.03% | 3.96% | 60.47% | 8.333% | 22.86%
Ryan | 7.477% | 41.41% | 10.81% | 5.941% | 19.07% | 52.78% | 19.05%
Andrew | 29.91% | 18.18% | 41.89% | 56.44% | 12.56% | 2.778% | 15.24%
Isaac | 23.36% | 14.14% | 20.27% | 33.66% | 7.907% | 36.11% | 42.86%
| Ryan | Isaac | Andrew | Greg
Initialising | 7.477% | 23.36% | 29.91% | 39.25%
Create the project plan. | 10.81% | 20.27% | 41.89% | 27.03%
Discover and understand the details of the problem | 41.41% | 14.14% | 18.18% | 26.26%
| 25% | 25% | 25% | 25%
| 25% | 25% | 25% | 25%
Design Components | 5.941% | 33.66% | 56.44% | 3.96%
Implement and Test | 19.07% | 7.907% | 12.56% | 60.47%
Monitoring and Controlling | 52.78% | 36.11% | 2.778% | 8.333%
Deploy | 19.05% | 42.86% | 15.24% | 22.86%
| 22.95% | 25.37% | 25.22% | 26.46%

## Total Hrs
Week Number | Initialising | Discover and understand the details of the problem | Create the project plan. | Design Components | Implement and Test | Monitoring and Controlling | Deploy | Weekly Total
Week 1 | 7.75 | 3.5 | 0 | 0 | 0 | 0.25 | 0 | 11.5
Week 2 | 6 | 3.5 | 3 | 5 | 2 | 3.5 | 0 | 23
Week 3 | 3 | 6 | 15 | 0 | 0 | 0.5 | 0 | 24.5
Week 4 | 0.5 | 0.25 | 15 | 1 | 3 | 5.5 | 0 | 25.25
Week 5 | 4 | 0.25 | 4 | 0 | 12 | 2.5 | 0 | 22.75
Week 6 | 3.5 | 2.25 | 0 | 0.5 | 10 | 1.5 | 0 | 17.75
Week 7 | 2 | 14.75 | 0 | 8 | 9 | 3 | 0 | 36.75
Week 8 | 0 | 10.25 | 0 | 7 | 11 | 2 | 0 | 30.25
Week 9 | 0 | 5.25 | 0 | 10 | 12 | 2 | 0 | 29.25
Week 10 | 0 | 2.25 | 0 | 8 | 17 | 1.5 | 0 | 28.75
Week 11 | 0 | 0.25 | 0 | 7.5 | 14.5 | 0.5 | 1 | 23.75
Week 12 | 0 | 1 | 0 | 3.5 | 17 | 5.75 | 0 | 27.25
Week 13 | 0 | 0 | 0 | 0 | 0 | 3.25 | 15.5 | 18.75
Week 14 | 0 | 0 | 0 | 0 | 0 | 4.25 | 12.75 | 17
Total | 26.75 | 49.5 | 37 | 50.5 | 107.5 | 36 | 29.25 | 336.5
| 15 | 20 | 32 | 12 | 201 | 60 | 37 | 377

## Costs
ID | Phase | Hours(4) | Cost (Business Analyst Rate(1)) | Cost (Programmer Rate(2)) | Cost (Project Manager Rate(3)) | Total Phase Cost | PM Hours | BA/ Programmer Hours | ID | Phase | Hours(4) | Cost (Business Analyst Rate(1)) | Cost (Programmer Rate(2)) | Cost (Project Manager Rate(3)) | Total Phase Cost
1 | Initialising | 26.75 | 997.325 | 0 | 505.8125 | 1503.1375 | 6.25 | 20.5 | 1 | Initialising | 15 | 2189.25 | 0 | 1213.95 | 3403.2
2 | Discover and understand the details of the problem | 49.5 | 2067.625 | 0 | 566.51 | 2634.135 | 7 | 42.5 | 2 | Discover and understand the details of the problem | 20 | 2919 | 0 | 1618.6 | 4537.6
3 | Create the project plan. | 37 | 1435.175 | 0 | 606.975 | 2042.15 | 7.5 | 29.5 | 3 | Create the project plan. | 32 | 4670.4 | 0 | 2589.76 | 7260.16
4 | Design Components | 70 | 0 | 2450 | 0 | 2450 | 0 | 70 | 4 | Design Components | 12 | 0 | 1680 | 0 | 1680
5 | Build all the program components, integrate and test. | 107.5 | 0 | 3762.5 | 0 | 3762.5 | 0 | 107.5 | 5 | Build all the program components, integrate and test. | 240 | 0 | 25200 | 0 | 25200
6 | Monitoring and Controlling | 36 | 1118.95 | 0 | 1052.09 | 2171.04 | 13 | 23 | 6 | Monitoring and Controlling | 21 | 3064.95 | 0 | 1699.53 | 4764.48
7 | Deploy | 29.25 | 875.7 | 0 | 910.4625 | 1786.1625 | 11.25 | 18 | 7 | Deploy | 37 | 5400.15 | 0 | 2994.41 | 8394.56
Totals |  | 356 | 6494.775 | 6212.5 | 3641.85 | 16349.125 |  |  | Totals |  | 377 | 18243.75 | 38556 | 10116.25 | 66916
Notes: | [6 empty] | 3400 | 19749.125 | Notes:
1. Business Analyst Hourly Rate-$48.65 (PayScale 2018). | [7 empty] | 379.875 | 1. Business Analyst Hourly Rate-$48.65 (PayScale 2018).
2. Programmer Hourly Rate-$35(PayScale 2018). | [8 empty] | 2. Programmer Hourly Rate-$35(PayScale 2018).
3. Project Manager Hourly Rate-$80.93(PayScale 2018). | [8 empty] | 3. Project Manager Hourly Rate-$80.93(PayScale 2018).
4. Phase hours sourced from Task Log Summary, refer Appendix XX. | [8 empty] | 4. Phase hours sourced from WBS, refer Table 1.
|  |  | 48.65 | 35 | 80.93 | [5 empty] | 377
[5 empty] | ` | [5 empty] | 0
19749.125
[6 empty] | 16349.125 | [6 empty] | 16729
|  | Labour | 16349.125 | [9 empty] | 3400
|  | Equipment | 3400 | [9 empty] | 20129
|  | Total | 19749.125
20129
|  |  | 379.875 | 0.018872
84.36
|  |  | 30.25 | 1167.6 | 0 | 505.8125 | 3403.2
|  |  | 33 | 1264.9 | 0 | 566.51 | 4537.6
|  |  | 40 | 1581.125 | 0 | 606.975 | 7260.16
|  |  | 70 | 0 | 1855 | 1375.81 | 1680
|  |  | 107.5 | 0 | 3465 | 687.905 | 25200
|  |  | 28 | 729.75 | 0 | 1052.09 | 4764.48
|  |  | 29.25 | 875.7 | 0 | 910.4625 | 8394.56
|  |  | 338 | 5619.075 | 5320 | 5705.565 | 16644.64

## Graph
0.42917 | 583.3333 | 72